MAYFLOWER CHURCH — NON-PASTORAL STAFF HIRING PROCESS One-Page Quick Reference • April 2026

Guiding principles: Process before urgency • Better no hire than the wrong hire • Character → Competence → Chemistry • Confessional alignment • Protect the flock (screening is not optional) • Same process, every candidate • Stewardship and transparency

| PHASE A — DISCERN & DEFINE |  |  |  |
| --- | --- | --- | --- |
| STAGE 1 Identify the Need Senior Pastor + Servants Council Gate: signed Position Authorization Memo | STAGE 2 Secure Funding Board of Finance Gate: Finance Memo; congregational vote if >$5K non-budgeted | STAGE 3 Write Position Description Search Team → Council Gate: PD approved, added to Manual | STAGE 4 Post & Invite Applications Search Team Gate: posting closed (21+ days), pool complete |
| PHASE B: RECRUIT & SCREEN ▶ PHASE C: INTERVIEW ▶ PHASE D: DECIDE & OFFER |  |  |  |
| STAGE 5 Pre-Screen Search Team Each applicant: Advance / Hold / Decline (within 7 days) | STAGE 6 Five Interviews 1 Screening • 2 Patterns • 3 Results • 4 References • 5 Relationships Same questions, every candidate. Scored on Appendix C rubric. | STAGE 7 References + Background Checks Search Team chair Verbal refs (3+) • Criminal • Sex offender registry • Role-specific checks • Continuous monitoring | STAGE 8 Recommend & Council Vote Search Team → Servants Council Elders confirm confessional alignment. Majority vote recorded. |
| PHASE E — ONBOARD & EVALUATE |  |  |  |
| STAGE 9 Written Offer Servants Council Chair drafts; Senior Pastor delivers. No verbal offers. Contingent on background clearance. 7–10 day response window. |  | STAGE 10 Onboard + 90-Day Probation Paperwork (I-9, W-4, M-4, direct deposit) before Day 1. 30 / 60 / 90 day check-ins. Council confirms continued employment at 90 days. |  |

| Decision Rights Servants Council directs all non-pastoral hiring (Bylaws Art. II §B 4(c)(9)) Board of Finance confirms funding; >$5K non-budgeted needs congregational approval Board of Elders confirms confessional alignment of top candidate Search Team (3–5 members) runs stages 3–8 under written charter Church Treasurer sets up payroll; Clerk archives personnel file | Typical Timeline (10–14 weeks) Week 1: Stages 1–2 — need + funding Weeks 2–3: Stage 3 — write Position Description Weeks 3–6: Stages 4–5 — post + pre-screen Weeks 6–9: Stage 6 — five-interview sequence Week 10: Stage 7 — references + background Week 11: Stages 8–9 — recommend, vote, offer Weeks 12+: Stage 10 — onboard + 90-day probation |
| --- | --- |

See full SOP for position description template, interview question sets, reference script, offer letter, onboarding checklist, and 90-day review template.  •  Adapted from "Streamline: Healthy Church Systems" and "The Guide to Healthy Church Operations," anchored in Mayflower Bylaws (March 2026).